Phase 1: Calibration & Feasibility (2 months)

Objective: Determine if signal exists and can be calibrated.

Dataset: TruthfulQA dev set (100 examples)
Model: Llama-2-7B
Annotation: 2 annotators, agreement > 85%

Subtasks:

1A: Perturbation Magnitude Calibration

Grid search: α ∈ {0.01, 0.025, 0.05, 0.1}

For each α:

- Compute I(t), q(t) on 50 examples

- Measure separability: AUROC between factual/hallucinating tokens

- Plot: I(t) and q(t) distributions by label

- Identify optimal α maximizing separability

Success: Single optimal α identified with AUROC > 0.70

Expected: α_opt ≈ 0.05

1B: Anisotropy & Layer-Wise Analysis

For selected model (Llama-7B):

- Measure isotropy of each layer

- Check if q(t) distributions shift systematically by layer

- Determine: Does single w_I work, or need layer-specific?

Success: Identify whether layer-dependent weighting improves signal

Expected: Layers 20–60 are most anisotropic; this affects q(t)

1C: Temporal Dynamics Validation

Generate 100 answers token-by-token.

For each answer:

- Plot I(t), q(t), Z(t) across all tokens

- Mark: When does hallucination start?

- Measure: Does Z peak BEFORE hallucination token?

Success: Median lead time > 0 tokens (any positive lead)

Expected: ~0.5–1 token median lead time

Phase 1 Success Criteria (GO/NO-GO):

GO if: 3/4 criteria met -

- Optimal α identified with clear separation

- Isotropy analysis shows pattern

- Median lead time > 0.3 tokens

- AUROC on 100 examples > 0.70

NO-GO if: <2/4 criteria met:

Pivot to alternative: Semantic perturbations (dropout, masking)

or different metrics (spectral features)

4.2 Phase 2: Validation Across Models & Datasets (2 months)

Objective: Prove signal scales and generalizes.

Models (3 families, 2 sizes each):

- Llama-2 (7B, 70B)

- Llama-3 (8B, 70B)

- Mistral (7B, 8×7B MoE)

Datasets (4 benchmarks + OOD):

Primary:

- TruthfulQA (800 examples) — in-distribution QA

- HaluEval (5,000 examples) — controlled hallucination generation

- CNN/DailyMail (1,000 samples) — summarization, long-form

- GSM8K (1,000 samples) — mathematical reasoning, OOD

Secondary (OOD Analysis):

- Shift from QA → summarization

- Shift from English → if multilingual models available

- Shift from factuality → instruction following

Subtask 2A: Benchmark Evaluation

For each (model, dataset) pair:

- Standard inference: Generate responses

- Token-levyel annotation: Mark hallucinated tokens

- Metric computation: I(t), q(t), Z(t) throughout sequence

- Temporal analysis: Identify Z peaks before hallucinations

5. Metrics:

  - AUROC: Distinguish factual from hallucinated tokens

  - AUPRC: Precision-recall on hallucination prediction

  - Lead time: Mean tokens before hallucination

  - FPR@TPR=0.8: False positive rate at 80% true positive rate

Success criteria:

  - AUROC ≥ 0.75 on TruthfulQA

  - AUPRC ≥ 0.70 on TruthfulQA

  - Median lead time ≥ 0.5 tokens

  - Generalization to HaluEval: AUPRC ≥ 0.65 (< 10% drop)

  - CNN/DailyMail: AUPRC ≥ 0.60 (performance acceptable on long-form)

Subtask 2B: CRITICAL - Creative vs. Erroneous Instability Ablation

Purpose: Prove I(t)+q(t) distinguishes creative generation from hallucination.

Detailed Protocol (Addressing Professor's Critique):

Step 1: Curate Creative Writing Benchmark

Select 100–150 prompts designed to elicit creative outputs:

  - Story generation: "Write a short story (50–100 words) about..."

  - Poetry: "Write a poem exploring the theme of..."

  - Paraphrasing: "Rephrase the following in a different style..."

  - Dialogue: "Write a conversation between..."

Constraint: Prompts should NOT have factual ground truth

(creativity is not hallucination if factually unconstrained)

Step 2: Human Annotation (Three Raters)

For each generated output, annotators rate:

| Dimension | Scale | Definition |
| --- | --- | --- |
| Creativity | 1–5 | Novelty, originality, imaginative departure from prompt |
| Factuality | 1–5 | Consistency with real world / claim support |
| Hallucination | Yes/No | Contains factually false statements |

Labels:

- Desired (Creative+Factual): Creativity ≥4, Hallucination=No

- False Positive (Creative+Hallucinating): Creativity ≥4, Hallucination=Yes

- Correct Factual: Creativity <3, Hallucination=No

IAA (Inter-Annotator Agreement): Fleiss' kappa > 0.60 required

If below: Refine annotation guidelines, re-annotate

Step 3: Measurement

For each generated output:

1. Compute I(t), q(t) trajectories (token-by-token)

2. Classify:

- High I(t), High q(t) → Creative branching (good instability)

- High I(t), Low q(t)  → Hallucination (bad instability)

- Low I(t), High q(t)  → Factual correctness (stable)

3. Correlation analysis:

  - P(Creative+Factual | High I, High q) = ?

  - P(Hallucination | High I, Low q) = ?

4. AUC: Can we distinguish Creative (High I, High q) from

Hallucinating (High I, Low q) using q(t) trajectory shape?

Step 4: Success Metrics

SUCCESS if:

  - AUC separating creative from hallucinatory outputs > 0.75

  - Precision(Creative | High I, High q) > 0.80

  - Recall(Creative | High I, High q) > 0.75

This proves: I(t)↑ + q(t)↓ = error, NOT creativity

Why This Matters:

- Addresses professor's "underdeveloped" criticism directly

- Demonstrates novel contribution beyond SSP/LSD

- Essential for claiming creative preservation

Subtask 2C: Baseline Comparisons (CRITICAL - Professor's Main Feedback)

Methods to Compare (All mandatory):

| Baseline | Paper | Type | Why Included |
| --- | --- | --- | --- |
| Entropy | (Standard) | Post-hoc | Baseline |
| DoLA | Chuang et al., ICLR 2024 | Layer contrast | SOTA post-hoc |
| Semantic Entropy | Farquhar et al., Nature 2024 | Multi-sample | High-performance baseline |
| LSD | arXiv:2510.04933 | Drift analysis | MOST SIMILAR prior work |
| SSP | Luo et al., June 2025 | Perturbation-based | CLOSEST competitor |
| INSIDE | arXiv:2405 | Eigenvalue | Complementary approach |
| SEP | arXiv (2024) | Probe-based | Semantic uncertainty |
| ITI | Li et al., NeurIPS 2024 | Intervention | Shows intervention possible |

Comparison Metrics:

For each baseline, measure on same test set:

  - AUROC (token-level classification)

  - AUPRC (practical metric for imbalanced data)

  - Lead time (for methods that enable prediction)

  - Computational overhead (actual measured)

  - Generalization to OOD data

  - Performance on creative tasks (if applicable)

  - Required computational resources (training, calibration, etc.)

Report: Tables with error bars (±95% CI) across all metrics

Fair Comparison Protocol:

- Same annotation labels (no label noise)

- Same held-out test set

- All methods allowed same computational budget (where applicable)

- Report both in-distribution and OOD results separately

Subtask 2D: Model Scaling & Generalization

Test whether phase 1 findings transfer:

1. Layer selection from 7B to applies to 70B?

  - Measure: Is top-K layer ranking similar?

  - Success: Rank correlation > 0.75

2. Optimal α from 7B → works for 70B?

  - Measure: Does α_opt differ across model sizes?

  - Success: Difference < 0.01 (stable across scale)

3. Weights (w_I) from one family → transfer to another?

  - Measure: Train on Llama-7B, test on Mistral-7B

  - Success: AUROC degradation < 0.05

4.3 Phase 3: Inference-Time Intervention (1 month)

Objective: Validate that early detection enables mitigation.

Intervention Strategy:

Algorithm: Adaptive Temperature Adjustment

When Z(t) > threshold_high (90th percentile):

- Increase softmax temperature T → T × 1.4 (locally, this token only)

- Re-sample next token from adjusted distribution

- Resume generation with standard T for following tokens

Threshold calibration:

  - Set to maximize: (% hallucination prevented) - (% false positives × cost)

  - Cost of false positive: Reduced fluency/creativity

Measurement Protocol:

Test set: 500 examples (TruthfulQA + HaluEval mix)

- Generate with LID + intervention ON

- Generate with standard inference (baseline)

3. Measure:

  - Hallucination rate reduction: (ε_baseline - ε_LID) / ε_baseline

  - False positive rate: % interventions on correct tokens

  - Fluency preservation: BLEU/ROUGE score change

  - Downstream task performance: If QA, measure accuracy impact

Success Criteria:

SUCCESS if:

  - Hallucination rate reduced by ≥ 15% points

  - False positive rate (intervention on correct text) < 10%

  - Fluency preserved (BLEU drop < 5%)

  - Lead time confirmed: Mean intervention 1–2 tokens before error

WEAK if:

  - Hallucination reduction < 10%

  - False positive rate > 15%

  - Still report as "detection without effective intervention"

4.4 Phase 4: Paper & Reproducibility (1 month)

- Final ablation studies

- Code cleanup & documentation

- Manuscript writing

- Prepare for submission

5. EXPECTED OUTCOMES & REALISTIC PROBABILITIES

5.1 Phase-by-Phase Outcomes

Phase 1 (Feasibility): 70% likely to clear GO threshold

If GO: Proceed to Phase 2 with confidence

If NO-GO: Pivot to semantic perturbations or spectral methods

(Still publishable, different approach)

Phase 2 (Validation): 55% likely to achieve >0.70 AUPRC + lead time

BEST CASE (25%):

- AUROC ≥ 0.78, AUPRC ≥ 0.75

- Lead time 1.5–2.5 tokens

- Creative ablation succeeds (AUC > 0.75)

- Generalizes to CNN/DailyMail, GSM8K

- Publication: NeurIPS

PARTIAL SUCCESS (45%):

  - AUPRC 0.65–0.75

  - Lead time 0.5–1.5 tokens

  - Creative ablation partial (AUC 0.65–0.75)

  - Generalization moderate

- → Publication: ICLR

WEAK SIGNAL (20%):

- AUPRC 0.60–0.65

- Lead time ~0.5 tokens

- Some creative/error distinction but weak

- Publication: EMNLP/Transactions

NO SIGNAL (10%):

  - AUPRC < 0.60

  - No reliable lead time

- Publication: Negative result paper

Phase 3 (Intervention): Conditional on Phase 2 success

IF Phase 2 is best/partial case:

  - 40% likely intervention helps (15–40% error reduction)

  - 30% likely marginal help (5–15% error reduction)

  - 30% likely no significant help

IF intervention helps:

→Publication quality bumps:  Workshop  -----  Conference,   Conference      -----    TopConf